# FarmBro Robotics — Master Project Plan

Consolidated planning document: production website, backend, payments, security, and launch timeline.
Prepared for client and development workflow. Editable — update dates and decisions as you go.

Document version: 1.0  |  Reference date: 21 September 2025  |  Repository: terraforge-robotics / FarmBro

# 1. Executive summary

FarmBro (package name: terraforge-robotics) is a marketing and lead-generation website for Indian-made agricultural robots. The frontend is largely complete. The business still needs a real backend: lead storage, WhatsApp notifications, payments (Razorpay), invoices, optional Google login, and production security.

Recommendation:

Move forward with the project in phases — do not attempt the full wishlist in one release.

Launch mid-October 2025 as Version 1 (MVP): live site + Enquiry + Order/Contact capture + client alerts.

Ship Oracle DB, Razorpay, PDF invoices, Google login, and hardening as Version 1.1 / 2 after launch.

Add a dedicated Enquiry form — buyers need to satisfy themselves before ordering high-ticket machines.

# 2. Current state (what exists today)

## 2.1 Technology stack

Frontend: React 19, Vite 7, Wouter routing, Tailwind 4, Framer Motion, Lenis smooth scroll.

UI: shadcn/Radix components, 7 languages (EN, HI, ML, TE, KN, GU, PA).

Backend today: Express serves static SPA only — no APIs, database, or CRM.

Catalog: client/src/data/catalog.ts (machines, attachments, slugs, media paths).

Lead capture: Order dialog + Contact form — toast only; data is not persisted or emailed.

## 2.2 Routes and pages

| Route | Purpose |
| --- | --- |
| / | Home — hero, machines, performance, pillars, mission, FAQ, order CTA |
| /farmbro | Store — lineup, compare, savings calculator, attachments |
| /farmbro/:slug | Product detail — gallery, specs, order CTA |
| /services | Services, warranty, warranty FAQ |
| /gallery | Filtered field photos + attachments |
| /about | Company story and principles |
| /contact | Contact form + direct lines |

## 2.3 Product catalog

| Machine | Type | Pricing (site) |
| --- | --- | --- |
| Remote Controlled Mulcher (Hybrid) | 4×4 UGV — Flagship | Price on request |
| Mulcher, Sprayer & Cargo Carrier | 6×6 UGV — Best seller | Price on request |
| Mini Mulcher (Electric) | 4×4 UGV — slopes to 45° | Price on request |
| Canopy Scout | Scouting drone | Price on request |

Attachments (indicative prices on site): Rotary tiller ₹42,000; Boom sprayer ₹38,000; Brush cutter ₹26,000; Field trailer ₹55,000.

## 2.4 Intended buyers

B2C — Progressive farmers (demos, training, WhatsApp follow-up).

B2B — Estates, cooperatives, contractors (fleet pricing, pilots).

Enterprise / Government — Civil and defence enquiry options in order form; FAQ mentions fleet and defence.

Note: Copy for “One store. Three kinds of buyers” exists in i18n but is not yet rendered on a page. Order dropdown already includes Fleet/B2B and Government options.

## 2.5 Gaps for production

No lead persistence (Oracle or other DB).

Placeholder email: hello@farmbro.example.

Media paths reference /images/agri and /videos — ensure real assets are deployed.

No Razorpay, invoices, or WhatsApp automation on sales.

No Google login or customer/admin portal.

Legal pages (privacy, terms) and full SEO per product/language.

# 3. Phased roadmap (marketing → platform)

## Phase 0 — Lock decisions (workshop)

Brand: FarmBro vs TerraForge.

Domain, business email, WhatsApp Business number.

Sales model: quote-first for machines; optional cart for attachments/deposits.

Buyer paths: farmer / fleet / government.

Geo: India-first vs export.

Content owners: photos, specs, pricing rules, legal, GST details.

Deliverable: one-page project brief signed by client.

## Phase 1 — Live-ready marketing + lead backend

Wire Enquiry, Order, and Contact forms to API → storage → WhatsApp/email to client.

Validation (Zod), rate limits, CAPTCHA/honeypot on public forms.

Replace placeholder contact details; privacy + terms stubs.

Real images/videos; sitemap, meta, OG tags.

Analytics + error monitoring.

Render three buyer audiences section OR remove unused copy.

Exit: every enquiry reaches the client and is stored.

## Phase 2 — Split buying journeys

B2C: Book field demo — crop, acres, district, machine interest.

B2B: Fleet pricing — company, GSTIN, machine count, sites, timeline.

Gov/Defence: separate institutional form — organisation, tender/RFP, compliance, NDA.

## Phase 3 — Product system of record

Move catalog to CMS or Oracle-backed admin (machines, attachments, specs, media).

PDF spec sheets; attachment configurator → indicative total → RFQ.

## Phase 4 — Sales ops (without full e-commerce for machines)

Lead pipeline: New → Demo → Quoted → Won/Lost.

Quote PDF generator; demo scheduling.

Dealer lead routing when applicable.

## Phase 5 — Trust and enterprise polish

Warranty/AMC PDFs; compliance hub (e.g. drone regulations).

Real testimonials/field footage only (no fabricated reviews).

Multi-language QA; accessibility; performance (video compression, CDN).

## Phase 6 — Scale (after Phases 1–4)

Dealer portal; fleet dashboard product login.

Spare parts with real checkout.

Tender document packs.

# 4. Target backend architecture (client requirements)

Browser (FarmBro React) → CDN/cache (e.g. Cloudflare) → API backend (Node: Express/Nest) → Oracle Database → Razorpay → WhatsApp Business API → PDF invoice service → Email (optional).

Roles (later): Guest, Customer, Dealer (optional), Admin (client — 2FA required).

Public pages stay open for SEO. Login for orders, invoices, and protected engineering assets — not required to browse machines.

## 4.1 Oracle Database (free tier ~20 GB)

Suitable for: users, leads, orders, payments, invoice metadata.

Not for storing all raw videos/3D files — use object storage + CDN; store URLs in Oracle.

Browser never connects to Oracle; only the API uses credentials from environment secrets.

## 4.2 Razorpay

Start with attachments and/or machine deposits — not full open checkout for lakh-rupee machines on day one.

Webhook is source of truth for payment.captured (not browser redirect alone).

Idempotent webhooks to avoid duplicate invoices.

## 4.3 WhatsApp on sale / enquiry

On enquiry: notify client with all form fields.

On successful payment: notify client + customer; attach or link invoice PDF.

Requires WhatsApp Business API (Meta) or approved provider (Twilio, etc.).

## 4.4 Google login and sessions

OAuth for customers/dealers after MVP — not required for mid-October launch.

httpOnly Secure cookies; CSRF protection.

Log IP and user-agent for audit only — not as sole identity verification.

## 4.5 PDF invoices

Generate server-side on payment success (GSTIN, HSN, place of supply per client legal input).

Send to buyer and to client (email and/or WhatsApp).

# 5. Security — what to build vs what to promise

## 5.1 Implement (real production security)

| Layer | Measures |
| --- | --- |
| Transport | HTTPS only, HSTS |
| Application | Input validation, parameterized SQL, CSRF, security headers |
| Auth | httpOnly cookies, session rotation, 2FA for admin |
| Abuse | Rate limits, CAPTCHA on forms/login, WAF (e.g. Cloudflare) |
| Secrets | Environment vault; never in frontend |
| Data | TLS to Oracle; encrypt sensitive PII columns if required; encrypted backups |
| Payments | Verify Razorpay webhook signatures; never trust client-submitted amounts alone |
| Media IP | High-res / 3D / CAD behind auth + short-lived signed URLs |
| Cache | CDN for static assets and safe public pages; do not cache authenticated/checkout responses |

## 5.2 Do not promise (browser limitations)

| Client ask | Reality |
| --- | --- |
| No screenshots | Cannot be enforced on web or mobile OS |
| No DevTools / no viewing code | Frontend is always inspectable; obfuscation only slows casual users |
| No image/video/3D download | Deterrents (watermark, no right-click) only; protect source files server-side |
| Unhackable / everything encrypted = no hack | Aim for strong, audited, least-privilege — not absolute guarantees |
| IP address as login verification | Use as fraud signal only; IPs change and VPNs exist |

Client messaging: “We protect payments, customer data, and engineering files with server security. We cannot guarantee blocking all screenshots on the open web. We lock down admin, APIs, and downloadable source assets.”

# 6. Enquiry form (recommended — add or clarify)

Yes — add or prominently label an Enquiry flow. High-ticket agri robots convert better enquiry-first than buy-now.

## 6.1 Suggested fields

Name, phone/WhatsApp, location/district

Crop or use case, acres (optional)

Interest type: demo / pricing / fleet / government / other

Free-text message

## 6.2 Relationship to existing forms

| Form | When to use |
| --- | --- |
| Enquiry | “I want information / demo / satisfy myself first” |
| Order request | “I know what I want — machine + quantity” |
| Contact | General topics — service, partnership, etc. |

Backend: single leads table with type = enquiry | order | contact.

# 7. Timeline and capacity (21 Sep → mid-October 2025)

## 7.1 Your available hours

| Period | Hours |
| --- | --- |
| Weekdays (~19 days × 1 hr/day) | ~19 hours |
| Weekends (3 × 2–3 hrs) | ~6–9 hours |
| Total to ~15 October | ~25–28 hours |

This is roughly one full-time engineering week — not enough for the complete backend + payments + login + fortress stack by mid-October.

## 7.2 What fits mid-October (MVP — Version 1)

Polish current site; dedicated Enquiry CTA/page

Forms → WhatsApp/email (+ simple storage if time allows)

Real media, privacy/terms, basic SEO

Form validation, HTTPS, basic rate limiting / CAPTCHA

Optional only if time remains: Razorpay deposit for attachments

## 7.3 What to schedule after launch (Version 1.1 / 2)

At 1 hr/day + weekends, expect roughly 4–6 additional weeks after mid-October for:

Oracle schema + full API

Razorpay webhooks + GST invoice PDFs

WhatsApp on paid orders

Google login + customer/admin portal

CDN, WAF, full hardening

## 7.4 Suggested week-by-week (MVP)

| Week | Dates (approx.) | Focus (~8–10 hrs each) |
| --- | --- | --- |
| Week 1 | 22–28 Sep | Client decisions; Enquiry UX; lead destination (WhatsApp/email) |
| Week 2 | 29 Sep – 5 Oct | Wire all forms; legal stubs; real assets; SEO basics |
| Week 3 | 6–12 Oct | Client UAT; mobile/bugs; security basics on forms |
| Buffer | 13–15 Oct | Final QA; content freeze; go live |

## 7.5 One-line message for client

“We launch mid-October with a production marketing site, Enquiry + Order capture, and WhatsApp/email alerts. Razorpay, invoices, Oracle backend, and Google login follow in Phase 2 immediately after launch.”

# 8. Implementation checklists

## 8.1 MVP launch checklist (mid-October)

[ ] Brand, domain, phone, WhatsApp confirmed

[ ] Enquiry form live with clear CTA

[ ] Order + Contact wired to client notifications

[ ] Leads stored (spreadsheet/API/DB — minimum viable record)

[ ] Privacy policy and terms published

[ ] Product images and videos on CDN/host

[ ] Sitemap and page meta tags

[ ] CAPTCHA or rate limit on public forms

[ ] Client UAT on real phones (regional languages spot-check)

## 8.2 Phase 2 checklist (post-launch)

[ ] Oracle: leads, orders, payments, users tables

[ ] API: POST /leads, POST /orders, Razorpay create + webhook

[ ] Invoice PDF template (GST fields from client)

[ ] WhatsApp templates approved by Meta

[ ] Google OAuth + customer “my orders/invoices”

[ ] Admin panel with 2FA

[ ] Signed URLs for protected media

[ ] Cloudflare CDN + WAF

## 8.3 Suggested database tables (Phase 2)

| Table | Purpose |
| --- | --- |
| leads | enquiry ¦ order ¦ contact; JSON payload; source page; created_at |
| users | Google id, email, role, created_at |
| orders | user_id, line items, amounts, status, razorpay_order_id |
| payments | order_id, razorpay_payment_id, status, captured_at |
| invoices | order_id, pdf_url, invoice_number, gst details |

# 9. What not to do

Full cart/checkout for machines before CRM and lead flow work.

Dealer portal before first conversions.

Another full visual redesign — brand direction is already strong.

More languages before EN/HI forms and flows are solid.

Fabricated testimonials or fake enterprise case studies.

Promising unhackable site or no screenshots to the client.

# 10. Next steps for developer

Run Phase 0 workshop with client; fill in Section 11 decision log.

Choose MVP lead path: WhatsApp-only vs email vs Oracle from day one.

Implement Enquiry + form wiring (Phase 1).

Set launch date with client as soft launch MVP; document Phase 2 start date.

Optional: request WhatsApp Business API and Razorpay merchant approval early (lead times).

# 11. Decision log (edit this section with client)

| Decision | Client answer | Date |
| --- | --- | --- |
| Official brand name |  |  |
| Production domain |  |  |
| Business email |  |  |
| WhatsApp Business number |  |  |
| GSTIN for invoices |  |  |
| Launch date (MVP) | Mid-October 2025 |  |
| Phase 2 start date |  |  |
| Oracle account owner |  |  |
| Razorpay account status |  |  |

— End of document —

You may edit any section in Microsoft Word, Google Docs (upload), or LibreOffice.